## Gantt Chart
Science Fund of the Republic of Serbia PROMIS 2023 Gantt Chart
* The form contains an example of correctly filled in fields. Delete examples when filling out Gantt Chart form but keep formulas.
Project proposal title:
Project proposal acronym:
Principal Investigator (PI):
| Description Months | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Work Package 1* | bar: 1 to 7
Subactivity 1.1 | bar: 1
Subactivity 1.2 | bar: 2; 4; 6
Subactivity 1.3 | bar: 6 to 7
Work Package 2* | bar: 1 to 16
Subactivity 2.1 | bar: 1 to 2
Subactivity 2.2 | bar: 2 to 5
Subactivity 2.3 | bar: 5 to 7
Subactivity 2.4 | bar: 7 to 10
Subactivity 2.5 | bar: 10 to 16
Work Package 3* | bar: 22 to 24
Subactivity 3.1 | bar: 22 to 24
Subactivity 3.2 | bar: 22 to 24
Subactivity 3.3 | bar: 23 to 24
Subactivity 3.4
Work Package 4*
Subactivity 4.1 | bar: 3 to 5; 16 to 19
Milestones and Deliverables*
Milestone 1.1 | bar: 7
Deliverable 1.1 | bar: 7
Milestone 1.2 | bar: 8
Deliverable 1.2 | bar: 8
Milestone 2.1 | bar: 17
Deliverable 2.1 | bar: 18
Milestone 3.1
Deliverable 3.1
Milestone 4.1 | bar: 5; 19
Deliverable 4.1 | bar: 5; 19
* Keep the same order of work packages, milestones and deliverables аs in F1a Project Description part A
| Personnel (% of working time)** | [24 empty] | Effective person-months
| Principal investigator (PI) | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 7.2
| Team Member 1 (TM1) |  | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 6.9
| Team Member 2 (TM2) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 24
| Team Member 3 (TM3) | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | [9 empty] | 4.5
| Team Member 4 (TM4) | 13: 10; 14: 10; 15: 10; 16: 10; 17: 10; 23: 10; 24: 10 | 0.7
| Team Member 5 (TM5) | 6: 5; 16: 5; 17: 5; 23: 5; 24: 5 | 0.25
| Total effective person-months | [24 empty] | 43.55
** Keep the same order of members of the project team in F1a Project Description part A and F2 Budget form
** Enter full names of team members as in F4 Applicant info form
** Keep same numbers of Effective months in project as in F2 Budget form